## Agile Product Backlog
PRODUCT BACKLOG
ID | USER STORY | SPRINT # | ASSIGNED TO | START | FINISH | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | STATUS
1 | As a user, I want to access the quiz without login in the application |  |  |  |  | 10 | 2 | 5 | Not Started
2 | As a user, I want to join the quiz with a simple identifier |  |  |  |  | 8 | 3 | 3 | Not Started | Completed
3 | As a user, I want to access the quiz on desktop devices |  |  |  |  | 10 | 1 | 10 | Not Started | Not Started
4 | As a user, I want to access the quiz on mobile devices |  |  |  |  | 9 | 1 | 9 | Not Started | In Progress
5 | As a user, I want to play the quiz by myself |  |  |  |  | 1 | n/a | n/a | Not Started
6 | As a user, I want to play the quiz in person |  |  |  |  | 3 | 1 | 3 | Not Started
7 | As a user, I want to play the quiz virtually |  |  |  |  | 10 | 5 | 2 | Not Started
8 | As a user, I want to play the quiz with my friends |  |  |  |  | 10 | 3 | 3 | Not Started
9 | As a user, I want to play the quiz with strangers |  |  |  |  | 1 | n/a | n/a | Not Started
10 | As a user, I want the quiz to include different types of questions, so that I don’t get bored |  |  |  |  | 7 | 5 | 1 | Not Started
11 | As a user, I want the quiz to include a wide range of questions, so that I don’t get the same ones as before |  |  |  |  | 8 | 2 | 4 | Not Started
12 | As a user, I want to text with the other players during the quiz |  |  |  |  | 1 | n/a | n/a | Not Started
13 | As a user, I want to voice chat with other players during the quiz |  |  |  |  | 1 | n/a | n/a | Not Started
14 | As a user, I want to video chat with other players during the quiz |  |  |  |  | 1 | n/a | n/a | Not Started
15 | As a user, I want to use hints and lifelines, so that I can still score when I don't know the answer |  |  |  |  | 1 | n/a | n/a | Not Started
16 | As a user, I want to be awarded with achievements and trophies when I score highly |  |  |  |  | 1 | n/a | n/a | Not Started
17 | As a user, I want to see the timer for each question |  |  |  |  | 10 | 2 | 5 | Not Started
18 | As a user, I want to see the progress of the quiz, so I can predict how long it will take to finish |  |  |  |  | 8 | 2 | 4 | Not Started
19 | As a user, I want the quiz to be mobile-friendly |  |  |  |  | 9 | 4 | 2 | Not Started
20 | As a user, I want to be able to see my score throughout the quiz |  |  |  |  | 7 | 3 | 2 | Not Started
21 | As a user, I want to be able to see the final ranking after the quiz is over |  |  |  |  | 10 | 2 | 5 | Not Started
| As a user, I can view the data regardless of colour blindness |  |  |  |  | 6 | 1 | 6 | Not Started
23 | As a user, I can navigate with a keyboard |  |  |  |  | 3 | 1 | 3 | Not Started
24 | As a host, I want to create a quiz with randomly generated questions, so that I don’t have to spend time on making my own |  |  |  |  | 9 | 4 | 2 | Not Started
25 | As a host, I want to create a quiz with custom questions |  |  |  |  | 4 | 3 | 1 | Not Started
26 | As a host, I want to name my quiz |  |  |  |  | 7 | 1 | 7 | Not Started
27 | As a host, I want to add different types of questions to my custom quiz |  |  |  |  | 3 | 2 | 2 | Not Started
28 | As a host, I want to decide how many rounds does the quiz have |  |  |  |  | 9 | 1 | 9 | Not Started
29 | As a host, I want to decide how many questions are in a round |  |  |  |  | 10 | 1 | 10 | Not Started
30 | As a host, I want to set how much time is given to players for answering each question |  |  |  |  | 10 | 1 | 10 | Not Started
31 | As a host, I want to pick the topic of the quiz |  |  |  |  | 5 | 3 | 2 | Not Started
32 | As a host, I want to choose how much time there is between rounds, so that I have the time in between to chat with other players |  |  |  |  | 10 | 1 | 10 | Not Started
33 | As a host, I want the identifier for my quiz to be easily distributable |  |  |  |  | 9 | 1 | 9 | Not Started
34 | As a host, I want to see if my friends have joined the quiz before starting it, so that I can make sure everyone is connected |  |  |  |  | 10 | 3 | 3 | Not Started
35 | As a host, I want to participate in the randomly generated quiz myself |  |  |  |  | 8 | 1 | 8 | Not Started
36
37 | As a developer, I would like to create a webpage as the main interface, so that the user can easily and quickly join a quiz | Sprint 2 |  |  |  | 10 | 8 | 1 | Not Started
38 | As a developer, I want to create unit tests for all functionality, so that I can ensure further development doesn't break any existing code | Sprint 1 |  |  |  | 9 | 3 | 3 | Not Started
39 | As a developer, I want to integrate the database, backend and frontend to allow the user a seamless experience | Sprint 2 |  |  |  | 10 | 4 | 3 | Not Started
40 | As a database designer, I want to come up with a clear view of how the database will be structured | Sprint 1 |  |  |  | 9 | 2 | 5 | Not Started
41 | As a backend developer, I want to host the website and the database on a server | Sprint 1 |  |  |  | 9 | 2 | 5 | Not Started
42 | As a backend developer, I want to network my website so multiple people can access the same quiz | Sprint 2 |  |  |  | 10 | 5 | 2 | Not Started
43 | As a developer, I want to design the program’s structure before starting to code | Sprint 1 |  |  |  | 7 | 1 | 7 | Not Started
44 | As a frontend developer, I want to optimise a webpage based on user and client feedback | Sprint 3 |  |  |  | 8 | 2 | 4 | Not Started
45 | As a developer, I want to design wireframes, so that changes can be made easily and quickly before creating a prototype | Sprint 1 | Frontend | Oct 6th | Oct 7th | 9 | 1 | 9 | Completed
46 | As a UX designer, I want to create a prototype, so that it can be presented to the client and the team before starting the development | Sprint 1 | Neja | Oct 7th | Oct 12th | 10 | 3 | 3 | In Progress
47 | As a UX designer, I want to create a product that is intuitive and easy to use | Sprint 1 | Neja | Oct 7th |  | 8 | 2 | 4 | In Progress
48
49
50
51