## Agile User Stories
USER STORIES
TASK ID | USER STORY | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | CONVERSATION | CONFIRMATION
1 | As a user, I want to access the quiz without login in the application | 10 | 2 | 5 | - Based on a session - If reloaded can't acces it again
2 | As a user, I want to join the quiz with a simple identifier | 8 | 3 | 3 | - Quiz ID with max. 6 numbers
3 | As a user, I want to access the quiz on desktop devices | 10 | 1 | 10 | - Website will be accessible from anywhere
4 | As a user, I want to access the quiz on mobile devices | 9 | 1 | 9 | - Website will be accessible from anywhere
5 | As a user, I want to play the quiz by myself | 1 | n/a | n/a | Discussed and decided outwith scope of project
6 | As a user, I want to play the quiz in person | 3 | 1 | 3 | - Not our primary user case, but can be used in person as well
7 | As a user, I want to play the quiz virtually | 10 | 5 | 2 | - Primary user case and unique selling point
8 | As a user, I want to play the quiz with my friends | 10 | 3 | 3 | - Anyone can join if they have the Quiz ID
9 | As a user, I want to play the quiz with strangers | 1 | n/a | n/a | Discussed and decided outwith scope of project - Strangers can join a quiz is the identifier is posted online
10 | As a user, I want the quiz to include different types of questions, so that I don’t get bored | 7 | 5 | 1 | - Currently have multiple choice, true/false, written answer and estimation questions
11 | As a user, I want the quiz to include a wide range of questions, so that I don’t get the same ones as before | 8 | 2 | 4 | - The dataset of questions should be 1000-2000
12 | As a user, I want to text with the other players during the quiz | 1 | n/a | n/a | Discussed and decided outwith scope of project
13 | As a user, I want to voice chat with other players during the quiz | 1 | n/a | n/a | Discussed and decided outwith scope of project
14 | As a user, I want to video chat with other players during the quiz | 1 | n/a | n/a | Discussed and decided outwith scope of project
15 | As a user, I want to use hints and lifelines, so that I can still score when I don't know the answer | 1 | n/a | n/a | Discussed and decided outwith scope of project
16 | As a user, I want to be awarded with achievements and trophies when I score highly | 1 | n/a | n/a | Discussed and decided outwith scope of project
17 | As a user, I want to see the timer for each question | 10 | 2 | 5 | - Timer will be visible on each question - When there are 5 or less seconds left on the timer it will turn a different colour
18 | As a user, I want to see the progress of the quiz, so I can predict how long it will take to finish | 8 | 2 | 4 | - Progress will be shown along the bottom of the screen - Indicators where in the round is this question positioned
19 | As a user, I want the quiz to be mobile-friendly | 9 | 4 | 2 | - Answeres will be positioned differently in mobile view so we can size up the buttons
20 | As a user, I want to be able to see my score throughout the quiz | 7 | 3 | 2 | - Scores will be shown at the end of each round
21 | As a user, I want to be able to see the final ranking after the quiz is over | 10 | 2 | 5 | - Final ranking will include the podium and scores for all the players
22 | As a user, I can view the data regardless of colour blindness | 6 | 1 | 6 | - Use https://www.toptal.com/designers/colorfilter/ | - Will run the system through colour blindness checkers online
23 | As a user, I can navigate with a keyboard | 3 | 1 | 3 | n/a | - Test the main webpage using the keyboard as navigation, ensure every box/button can be accessed/edited
24 | As a host, I want to create a quiz with randomly generated questions, so that I don’t have to spend time on making my own | 9 | 4 | 2 | - Primary unique selling point - Questions will be randomly selected from out database - Host can pick how many rounds and how many questions there is
25 | As a host, I want to create a quiz with custom questions | 4 | 3 | 1 | - Host can also create a custom quiz - Quiz has to be downloaded as a csv file - When the host is ready to start the quiz, they can upload the file
26 | As a host, I want to name my quiz | 7 | 1 | 7 | - Quizzes are named so the people joining can make sure they are in the right quiz
27 | As a host, I want to add different types of questions to my custom quiz | 3 | 2 | 2 | - Custom quiz can include all the possible question types
28 | As a host, I want to decide how many rounds does the quiz have | 9 | 1 | 9 | - Sets before starting the quiz
29 | As a host, I want to decide how many questions are in a round | 10 | 1 | 10 | - Sets before starting the quiz
30 | As a host, I want to set how much time is given to players for answering each question | 10 | 1 | 10 | - All questions have the same amount of time - Time is chosen by the host before starting the quiz - In seconds
31 | As a host, I want to pick the topic of the quiz | 5 | 3 | 2 | - Not decided if we want to implement this yet
32 | As a host, I want to choose how much time there is between rounds, so that I have the time in between to chat with other players | 10 | 1 | 10 | - Sets before starting the quiz - in minutes
33 | As a host, I want the identifier for my quiz to be easily distributable | 9 | 1 | 9 | - Identifier is max. 6 digits long - Can be copied and sent to everyone joining
34 | As a host, I want to see if my friends have joined the quiz before starting it, so that I can make sure everyone is connected | 10 | 3 | 3 | - Before host starts the quiz they can see how many people joined
35 | As a host, I want to participate in the randomly generated quiz myself | 8 | 1 | 8 | - The host can choose to participate in the quiz
DEVELOPMENT TASKS
TASK ID | USER STORY | PRIORITY | COMPLEXITY | RETURN ON INVESTMENT | CONVERSATION | CONFIRMATION
36 | As a developer, I would like to create a webpage as the main interface, so that the user can easily and quickly join a quiz | 10 | 8 | 1 | - Using ASP NET
37 | As a developer, I want to create unit tests for all functionality, so that I can ensure further development doesn't break any existing code | 9 | 3 | 3 | - Framework used Xunit
38 | As a developer, I want to integrate the database, backend and frontend to allow the user a seamless experience | 10 | 4 | 3 | - Research sturctures we can use to connect between each other - Working together to create compatible code
39 | As a database designer, I want to come up with a clear view of how the database will be structured | 9 | 2 | 5
40 | As a backend developer, I want to host the website and the database on a server | 9 | 2 | 5 | - Set up the database and website on Azure - Using a mySQL database and hosted on MS Azure | - Test if website works through the link
41 | As a backend developer, I want to network my website so multiple people can access the same quiz | 10 | 5 | 2 | - Research client-side / server-side programs
42 | As a developer, I want to design the program’s structure before starting to code | 7 | 1 | 7 | - Class diagrams - Algorithms - Winning logic
43 | As a frontend developer, I want to optimise a webpage based on user and client feedback | 8 | 2 | 4 | - Test accessibility features - Collect client feedback from the client meetings - Collect user feedback with user testing - Update the application based on it
44 | As a developer, I want to design wireframes, so that changes can be made easily and quickly before creating a prototype | 9 | 1 | 9 | - Quick wireframing sketches by the frontend group
45 | As a UX designer, I want to create a prototype, so that it can be presented to the client and the team before starting the development | 10 | 3 | 3 | - Interactive protoype created in Axure RP
46 | As a UX designer, I want to create a product that is intuitive and easy to use | 8 | 2 | 4 | - Research what is the best way to present questions and answers - Does colour / shape make a difference - What is the thing that makes the quiz fun for the user?